## Sheet1
Index | Author (who must do it) | Task (what must be done) | Open date (when was it registered) | Close date (when was it done) | State | Note (optional)
1 | Antmann | Do the tasks said in last meeting (15/2/22) | 2022-03-22 00:49 | 2022-03-31 12:00 | Closed | Tasks start from this point, at each meeting, tasks to do till next meeting, or tasks added along the way will be added in this document
2 | Antmann | Doc 1: Put the "models" part in an initial state | 2022-03-31 12:00 |  | Opened
3 | Antmann | Doc 1: Put the "sources menu" part in an initial state | 2022-03-31 12:00 |  | Opened
4 | Antmann | Doc 1: Put the "sources content menu" part in an initial state | 2022-03-31 12:00 |  | Opened
5 | Antmann | Doc 1: Put the "thesis menu" part in an initial state | 2022-03-31 12:00 |  | Opened
6 | Antmann | Doc 1: add the data structures entries in a "global/overview" part of the document | 2022-03-31 12:00 |  | Opened
7 | Antmann | Doc 1: add the content of the drafts of the past meetings in the document | 2022-03-31 12:00 |  | Opened
8 | Antmann | Doc 1: add the content of the paper drafts in the document | 2022-03-31 12:00 | 2022-04-12 | Closed | Transfered paper drafts to a draft document in folder "Draft"
9 | Antmann | Prepare next meeting | 2022-03-31 12:00 |  | Opened
10 | Antmann | Push changes to origin | 2022-03-31 12:00 |  | Opened
11 | Antmann | Give signal to Tillmann that the document is intialized | 2022-03-31 12:00 |  | Opened
12 | Antmann | Yellow highlight the temporary/non approved/unsure stuff | 2022-03-31 12:00 |  | Opened
13 | Tillione | Wait for further info | 2022-03-31 12:00 |  | Opened | Waiting for task 11
14 | Antmann | Start payment (12/h) | 2022-03-31 12:00 | 2022-04-07 | Closed
15 | Antmann | Retrieve vocals on instagram from Adrien for the original vision | 2022-04-07 16:31 |  | Opened
16 | Tillione | Contact wordpress support to understand what wordpress subscription offers exactly (all plugins? Only access to plugins and then u have to pay for each?...) | 2022-04-08 17:34 | 2022-04-07 16:00 | Closed | DshÖrman forum
17 | Antmann | Put Macron boomer story in introduction of doc 1 | 2022-04-07 16:00 |  | Opened
18
19
20
21
22
23

## List
State | Author
Opened | Tillione
Started | Antmann
Paused
Cancelled
Closed